## Sheet1
Role | Responsibilities
System Owner / Business Owner Peter | Make strategic business decisions supporting the project objectives
Communicate business resource constraints
Furnish business resources as needed to accomplish project deliverables
Prioritize work across the business team to ensure project work has the right level of urgency and expectations are clear
Formally certify the system after user acceptance testing has been complete
Formally approve business oriented deliverables
Assign Business SME's to project team
Business Lead Theresa | Communicate the high level needs to the BSC to kick off the onboarding and initiation of a project
Main liaison between the BSC and all other stakeholders on the business side.
Facilitate the gathering of Business System requirements with the BSA and Project Manger for ALL stakeholders
Key representative from the business directly working with BTS on all project deliverables and actions.
Becomes the strongest SME of the system and main advocate for the system
Provides business direction and clarification around requirements during development.
Facilitates User Acceptance testing
Generates user acceptance testing results
Main ambassador during rollout and helps team members with the adjustment to the new system or process
Responsible for business process mapping
Responsible for training
Responsible for roll out strategy and plan along with communication plan around rollout
PM Tom | Facilitate agreement on project approach, elevates issues to BSC, and manages overall project: resources, finances, and schedule to accomplishment of project objectives.
Furnish regular periodic project status updates in timely manner
Facilitates work plan development to provide project assignments and guidance along with project performance feedback for all resources in order to respond to elevated issues in a timely manner
Assign or redistribute project work to project team members
Oversee and facilitate the project change management needs and facilitates all communication with change
Facilitate weekly meetings with project team and monthly steering committee meetings
Provide meeting minutes for weekly status and Steering committee meetings around decisions, issues, and risks discussed
Facilitates ALL changes to the project plan and changes to project schedule along with changes to general requirements
BSA Mani | Project owner of documentation for ALL the project requirements across all stakeholders
Business process SME and understand the system and how it fits into the business need
BTS advocate for the system and the business process it will improve
Assist business personnel to understand BTS perspectives and changes
Support PM with detailed status updates and facilitates smaller more detailed daily meetings 1 on 1 with business project members
Assist with UAT planning and preparation
BSC Ed | Resolve Strategic issues with approach or plan a tactical pivot for execution to meet deadlines or goals originally benchmarked
Works with PM to escalate issues when required to the Steering Committee
Elevate external issues that could affect the project such as shared funding flux or software / hardware changes on BTS infrastructure
Closely involved in the strategic approach around the technology chosen and the landscape in BTS for that technology
Main line of contact for the PM to escalate or reach out to for extra support from BTS or extra support on the project team
Understands the business process and how the solution will fill the need along with the intended use cases for the new system
Main point of contact for the business owner as a trusted BTS partner in regards to a shared vision, approach and strategy for the solution moving beyond the project deadlines